Planning Model Worksheet (Classroom Instructional Focus)

| Principal Investigator(s): Jo Bell Whitlatch & Yu Zhang Name of Library: Haui’an Yizhong, Evergreen Education Foundation & CERLS | Date: 4/16/11 |
| --- | --- |
| I. Project Purpose Statement |
| High-level design of the project. Refer to Module B. Plan “Program Purpose”.You can revise and polish this section by summarizing Part II, III and IV later. |
| What is the project’s name? | Project Planning and Evaluation – OBPE Training |
| We do what? (Brief statement; Details see Part IV) | We provide training in planning, building, and evaluating projects. |
| For whom? (Brief statement; Try to list all major beneficiaries.Details see Part II and III) | Evergreen school and public library staff who are initiating special projects |
| For what outcomes/benefits? (Brief statement; Details see Part II and III) (Validity check: The outcomes must include at least one item related to information literacy improvement of the major beneficiary.) | To develop skills related to initiating, implementing, and evaluating special projects |
| What is the role of the Library? (Describe how the library be involved in supporting outcomes related to information literacy) | As part of the training, workshop participants will define the role of the library in reaching their individual project outcomes. |
| II. Audience Needs Assessment Refer to Module B. Plan “Audience Needs” and “Audience Considerations”. |
| Who are the audiences? (Audiences are major beneficiaries.) | Evergreen school and public library staff who are interested in initiating special projects |
| What are the needs of the audience? (Please explain how assessed.) (Validity check: The needs must include at least one item belonging to information literacy improvement of the audience.) | Become more familiar with project planning, implementation, and evaluation practices and have an opportunity to gain practical experience in planning a project of particular interest to each member of the audience. Information source: Informal conversations with school personnel over several years. Staff in Evergreen schools and libraries have expressed desire for more training in areas related to management. Informal conversations with small project team: Judged by the small project proposals and reports, that the local team for small projects need such training. |
| What are some audience considerations? (Including stakes or risks, constraints, etc.) | Limited access to learning opportunities for improving skills; Limited time to devote to training and development, given the press of daily responsibilities; Limited access to most relevant project planning information. |
| What solution fulfills the needs? | A practical interactive workshop with a combination of presentations and opportunities to practice relevant skills and receive feedback on level of skills. |
| What outcomes of the solution answer the needs? | Workshop participants demonstrate basic understanding of Outcomes Based Planning and Evaluation by successfully completing a logical planning model worksheet with all essential fields correctly completed. |

| III. Project Partners and Stakeholders Refer to Module B. Plan “Stakeholders”. |
| --- |
| Who are the Partners? | CERLS Huai’an No. 1 High School (Huai’an Yizhong) |
| What are their interests? (Explain how assessed) | CERLS – funding special projects that have a high probability of being successful and enhancing student and community educational opportunities. Information Source: previous experience with workshops, conferences and school visits by Board members. Huai’an Yizhong – Form a strong partnership with CERLS to gain more access to resources and expertise for investigative learning. Also having teachers attend the workshop to learn Outcomes Based Planning and Evaluation. |
| What are the stakes or risks of each partner? (Explain how assessed) | CERLS – Funding, the training team’s time and efforts for design and conduct the training Huai’an Yizhong – investment in conference planning and support |
| What outcomes of the solution satisfy their interests? | CERLS – Successful and well developed proposals using the logical planning model that have a high potential for success and do enhance student and community educational opportunities Huai’an Yizhong – Workshop participants benefit from the above outcome. Also help CERLS in methodology development will help CERLS in accumulating and reaching out to resources and expertise for investigative learning. |
| Who are the Stakeholders other than audiences and partners? | Community in which projects take place; however analysis of these stakeholders has not been conducted |
| What are their interests? (Explain how assessed) | No analysis done |
| What are the stakes or risks of each above stakeholder? (Explain how assessed) | No analysis done |
| What outcomes of the solution satisfy their interests? | No analysis done |
| IV. Project Elements Refer to Module C. Build. In this Part, we derive Learning Objectives => Instructional Services =>Activities => Inputs and Work products of Activities. |
| Index | Learning Objectives (Expected Outcomes) Index labeled as L1, L2, … | Supporting Instructional Services (Index into Instructional Service Table) |
| L1 | Workshop participants write project purpose statements that identify what they do, for whom, and for what outcomes/benefits | S1 S2 S3 |
| L2 | Workshop participants define the involvement of the library in reaching project goals that are related to information literacy. | S1 S2 S3 |
| L3 | Workshop participants list the project audience(s), major needs, and considerations | S1 S2 S3 |
| L4 | Workshop participants identify an appropriate solution | S1 S2 S3 |
| L5 | Workshop participants identify project partners, their interests, their stakes/risks, and the project outcomes of interest to each partner | S1 S2 S3 |
| L6 | Workshop participants create outcomes – learning objectives/services – and the supporting activities necessary | S1 S2 S3 |
| L7 | Workshop participants analyze level of risk for all project activities | S1 S2 S3 |
| L8 | Workshop participants identify all necessary inputs essential for project success. | S1 S2 S3 |
| L9 | Workshop participants define work products of the activities, including assessment activities | S1 S2 S3 |
| L10 | Workshop participants select appropriate indicators, people to whom applied, source of data, and data collection interval in order to evaluate outcomes. | S1 S2 S3 |
| L11 | Workshop participants report an improved understanding of Outcomes Based Planning and Evaluation concepts | S1 S2 S3 |
| Index | Instructional Services Index labeled as S1, S2, … | Supporting Activities (Index into Activities Table) |
|  | Presentation by instructor of Modules A-F to the workshop trainees | A1 A3 A4 A6 |
|  | Discussion group sessions participated by the workshop trainees to support each trainee completing a planning model worksheet for his/her own project. | A5 |
|  | OBPE course contents hosted on wiki, including interactive quizes for the trainees to access. | A2 |
| Note: All activities need to be resolved into low risk level by adding inputs/resources or assisting activities. So activity listing may go through several risk-control iterations. |
| Index | Activities Index labeled as A1, A2, …for activities and AS1, AS2… for assessment activities. | Schedule | Risk Assessment | Inputs Needed (Index into Inputs Table) | Work products Produced (Index into work product Table) |
|  | The training team adapts the IMLS Shaping Outcomes course, esp. the logical planning model to better suit the EEF libraries’ needs, e.g. adjusting the order of Section IV of the planning model so it is easier to understand, adding risk management of activities, linking the data source of outcomes evaluation indicators to work products of activities, converting all existing case studies to revised logical planning model, introducing new concepts into the glossary, etc. | 2011.2-2011.3 | low | I1 | P1 |
|  | The training team upload the course contents to EEF wiki, and maintain the wiki for any updated course contents all through the project. | 2011.2 – 2011.5 | low | I1 | P2 |
|  | The training team produces case studies based on past EEF projects. | 2011.2-2011.3 | low | I1 | P1 |
|  | The training team translates all course materials in English to Chinese. | 2011.4-2011.5 | low | I1 | P1 |
|  | The training team designs the group discussion sessions to facilitate full participation and peer review of trainees’ work. | 2011.4-5 | low | I1 | P3 |
|  | The instructor prepares power point slides | 2011.5 | low | I1 | P4 |
|  | The training team evaluates OBPE workshop outcomes | 2011.6 | low | I1 | P5, P6 |
| Index | Inputs (facility/hardware/software resources; also people, materials, standards, and information resources required by the activities.) Index labeled as I1, I2, … | Units and Counts |
|  | Besides preparing for the training, the training team includes the instructor, teaching assistants to conduct the training at the workshop. | No. of manhours provided |
| Index | Work products of the activities, including assessment activities Index labeled as P1, P2, … | Units and Counts - Outputs |
|  | OBPE textbook with Module A-F, Glossary, logical planning model worksheet template, and existing and EEF case studies (English and Chinese version) | One set |
|  | OBPE wiki | One website |
|  | Group discussion session design |  |
|  | Power point slides for Modules A-F | One set |
|  | Outcomes/Learning Objectives 1-10 Scoring Rubric | One rubric |
|  | Evergreen 2011 Workshop Feedback Form (OBPE portion) | One form |

| V. Outcomes Evaluation |
| --- |
| Refer to Module D. Evaluate. To evaluate outcomes, we select indicators to demonstrate changes of target audience, then determine data sources (certain work products from project activities, including assessment activities) to derive these indicators, and target of these indicators in order to say that the outcomes have been achieved. Data sources are produced by activities. So for “When to collect (the Data Source)?”, refer to the “Schedule” column of the corresponding activity. |
| Outcome 1: Workshop participants write project purpose statements that identify what they do, for whom, and for what outcomes/benefits |
| Indicator(s) | Applied to | Data Source (index to Work product Table) | Data Interval (When to collect?) | Target |
| % of participants who are proficient | Workshop participants | P5 Scoring Rubric | Day 3 |  |
| Outcome 2: Workshop participants define the involvement of the library in reaching project goals that are related to information literacy. |
| Indicator(s) | Applied to | Data Source (index to Work product Table) | Data Interval (When to collect?) | Target |
| % of participants who are proficient | Workshop participants | P5 Scoring Rubric | Day 3 |  |

| Outcome 3: Workshop participants list the project audience(s), major needs, and considerations |
| --- |
| Indicator(s) | Applied to | Data Source (index to Work product Table) | Data Interval (When to collect?) | Target |
| % of participants who are proficient | Workshop participants | P5 Scoring Rubric | Day 3 |  |
| Outcome 4: Workshop participants identify an appropriate solution |
| Indicator(s) | Applied to | Data Source (index to Work product Table) | Data Interval (When to collect?) | Target |
| % of participants who are proficient | Workshop participants | P5 Scoring Rubric | Day 3 |  |
| Outcome 5: Workshop participants identify project partners, their interests, their stakes/risks, and the project outcomes of interest to each partner |
| Indicator(s) | Applied to | Data Source (index to Work product Table) | Data Interval (When to collect?) | Target |
| % of participants who are proficient | Workshop participants | P5 Scoring Rubric | Day 3 |  |

| Outcome 6: Workshop participants create outcomes – learning objectives/services – and the supporting activities necessary |
| --- |
| Indicator(s) | Applied to | Data Source (index to Work product Table) | Data Interval (When to collect?) | Target |
| % of participants who are proficient | Workshop participants | P5 Scoring Rubric | Day 3 |  |

| Outcome 7: Workshop participants analyze level of risk for all project activities |
| --- |
| Indicator(s) | Applied to | Data Source (index to Work product Table) | Data Interval (When to collect?) | Target |
| % of participants who are proficient | Workshop participants | P5 Scoring Rubric | Day 3 |  |

| Outcome 8: Workshop participants identify all necessary inputs essential for project success. |
| --- |
| Indicator(s) | Applied to | Data Source (index to Work product Table) | Data Interval (When to collect?) | Target |
| % of participants who are proficient | Workshop participants | P5 Scoring Rubric | Day 3 |  |
| Outcome 9: Workshop participants define work products of the activities, including assessment activities |
| Indicator(s) | Applied to | Data Source (index to Work product Table) | Data Interval (When to collect?) | Target |
| % of participants who are proficient | Workshop participants | P5 Scoring Rubric | Day 3 |  |

| Outcome 10: Workshop participants select appropriate indicators, people to whom applied, source of data, and data collection interval in order to evaluate outcomes. |
| --- |
| Indicator(s) | Applied to | Data Source (index to Work product Table) | Data Interval (When to collect?) | Target |
| % of participants who are proficient | Workshop participants | P5 Scoring Rubric | Day 3 |  |

| Outcome 11: Workshop participants report an improved understanding of Outcomes Based Planning and Evaluation concepts |
| --- |
| Indicator(s) | Applied to | Data Source (index to Work product Table) | Data Interval (When to collect?) | Target |
| % of participants who report improved understanding of Outcomes Based Planning and Evaluation concepts | Workshop participants | P6 Evergreen 2011 Workshop Feedback Form | Day 3 |  |

Outcomes/Learning Objectives 1-10 Scoring Rubric

| Learning Objective | Proficient (4) | Partially Proficient (2) | Incomplete (0) | Credits (6 possible) |
| --- | --- | --- | --- | --- |
| L1 Project Purpose | What, for Whom, and for What Outcomes are clearly stated | Some statements are not specific | None of statements are specific |  |
| L2 Library Involvement | Provide clear statement of role of the library in the project | Role of library in project not well defined and/or does not appear essential to support project | No mention of role of the library |  |
| L3 Audience | Audience, their needs, and considerations thoughtful, thorough and specific | Information on audience, their needs, and considerations not very detailed | No information on one or more of these topics: audience, their needs or considerations |  |
| L4 Solution | Solution appears practical, with adequate resources, and appropriate based on informal assessments of audience, their needs and considerations | Solution may work but not well linked to assessments of audience, their needs and consideration | Solution vague with no information linking solution to audience needs and considerations |  |
| L5 Partners | Clear statements of project partners, their interests, risks/stakes, and outcomes of interest | Some statements are not specific | None of the statements are specific |  |
| L6 Outcomes | Outcomes/Learning Objectives statements identify a change in the audience’s skills, attitudes, knowledge, behaviors, or status/life condition. | Some but not all outcomes statements identify changes in people. | None of the statements identify desired changes in people. |  |
| L7 Risk Analysis | Clear statement of level of risk for each activity and identification of risk as low, medium or high, with discussion of how to limit risks for high risk activities. Also risk estimation is practical. | Not all activities are analyzed for risk and/or limited explanation for high risk activities | No analysis of risk for the majority of activities |  |
| L8 Inputs | Comprehensive listing of all inputs needed for project, including facility/hardware/software resources, people, materials, standards, and information resources. | Most essential resources listed; some categories not mentioned, but appear needed as inputs/resources for supporting project activities. | Many categories of resources, which are necessary for project support, are not mentioned. |  |
| L9 Work Products | Comprehensive list of all work products resulting from project activities | Lists most but not all work products resulting from activities | Many work products that should result from activities are not listed |  |
| L10 Evaluation | For each outcome, indicator, people applied to, data source and data interval clearly stated | Many indicators, data sources, and data intervals incomplete | Most indicators, data sources and data intervals incomplete |  |

VI. Budget Based on the Inputs Table in Part IV, estimate the budget needed and list the detailed budget items. Please use the budget template in Excel format, and under each resource category, list the resource items and estimated budget. The expense structure shall meet the requirements specified by EEF. For EEF small projects, the EEF requirements are detailed in EEF Library Small Project Guide of the corresponding year.

| VII. Division of Responsibilities among Partners |
| --- |
| Name of partner | List of Responsibilities | Responsible person’s Signature | Date |
| CERLS | Funding for the workshop. The training team designs and conducts the training (all the activities A1-A6, AS1) |  |  |
| Huai’an Yizhong | Search for and reserve venue, hotel, meal, refreshments service, land transportation service, etc. to enable this workshop. |  |  |

# Comments

Means “certain”?